Purpose: 	To create a “script” for your building/district implementation of the KCCS.

Implementation Component:

X	Managing Change

- Instructional Practices

- Curricula

- An Assessment System

- Professional Learning

- Communications & Resources

Directions: 	1. Using this form as a template, develop a work plan for each goal identified through

the needs assessment process. Modify the form as needed to fit your unique context.

Completing the form electronically allows cells of the chart to be expanded.

2. Distribute copies of the implementation plan to the members of the collaboration.

3. Keep copies handy to bring to meetings to review and update regularly. You may

decide to develop new plans for new phases of your implementation.

Goal:  Continual communication between staff and stakeholders to ensure understanding and use of KCCS

Results/Accomplishments:

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources - Resources Available - Resources Needed (financial, human, political & other) | Potential Barriers - What individuals or entities might resist? - How do we address this resistance? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| Step 1: District-Level PLCs – Grade Level Focus – focus on parts of standards and share resources at each meeting | Language Arts Team will facilitate and provide resources | Each Month for 30 minutes – we will decide the timeline next week | A. Angie will make sure district PLCs have language arts focus B. Documents, timeline, | A. Time & Getting administrators involved B. Make sure to have agenda, set norms, stay on task, have someone take notes & Angie will focus on training | Make sure to have agenda, set norms, stay on task, have someone take notes **Make sure we send a document to everyone about expectations of teachers and students (ie – guided reading levels/ running records and benchmarking requirements) **We will decide on who communicates when we meet next week |
| Step 2: Do get re-acquainted with the standards activities at beginning of the year | Language Arts Team will facilitate and provide resources |  | A. Highlighting activity Character Association B. | A. B. |  |
| Step 3: |  |  | A. B. | A. B. |  |
| Step 4: |  |  | A. B. | A. B. |  |
| Step 5: |  |  | A. B. | A. B. |  |

Evidence Of Success (How will you know that you are making progress? What are your benchmarks?)

Evaluation Process (How will you determine that your goal has been reached? What are your measures?)