Purpose: 	To create a “script” for your building/district implementation of the KCCS.

Directions: 	1. Using this form as a template, develop a work plan for each goal identified through

the needs assessment process. Modify the form as needed to fit your unique context.

Completing the form electronically allows cells of the chart to be expanded.

2. Distribute copies of the implementation plan to the members of the collaboration.

3. Keep copies handy to bring to meetings to review and update regularly. You may

decide to develop new plans for new phases of your implementation.

Goal:  Implement at least 50% of the Common Core concepts while continuing with State Standards by the

end of the 2012-2013 school year.

Results/Accomplishments:

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources Resources Available Resources Needed (financial, human, political & other) | Potential Barriers What individuals or entities might resist? How do we address this resistance? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| Step 1: Compare curriculum mapping with Common Core to see what standards were added or shifted. | Teachers Administrators | By January 2013 *half-day in-service | A. Curriculum maps, CC flipcharts, CC binder, KSDE website B. Time | A. Time B. Provide in-service hours |  |
| Step 2: Align curriculum | Teachers | By May 2013 *one staff meeting a month | A. CC flipcharts, KSDE website, template B. Time | A. Time B. Provide in-service hours or staff meeting time | *inform parents of standards change *communicate with each other through e-mails and staff meetings |
| Step 3: Evaluate resources | Teachers Administrators | By May 2013 *half-day in-service | A. Current textbooks and manipulatives B. Money | A. Money, buy-in from school board, time B. Get creative with what resources we currently have |  |

| Step 4: In-service training on implementing Common Core strategies and questioning techniques. | Teachers Administrators SHESC | Ongoing during 2012-2013 school year *once a month | A. SHESC, KSDE website, Professional articles B. Time, money for presenters | A. School board, time, money B. Communicate with board, administration, and parents |  |
| --- | --- | --- | --- | --- | --- |
| Step 5: Implement strategies | Teachers | By August 2013 *Daily | A. Dependent upon training and resources provided B. Ongoing feedback between teachers and administration | A. Buy-in, lack of training, lack of resources B. Constant communication, ongoing feedback |  |
| Step 6: Review/Add Common Core strategies. | Teachers Administrator | Ongoing during 2013-2014 school year *bi-weekly grade-level meetings or staff meetings | A. SHESC, KSDE website, professional articles B. Time during scheduled meetings to discuss and share | A. Time B. Schedule time into meetings |  |

Evidence Of Success (How will you know that you are making progress? What are your benchmarks?)

Checklist completed by each teacher throughout the school year indicating which Common Core standards were taught during the school year.

Evaluation Process (How will you determine that your goal has been reached? What are your measures?)

Each teacher completed a Common Core checklist with at least 50% of the standards checked off.

# Text boxes

Implementation Component:

- Managing Change

X    Instructional Practices

- Curricula

- An Assessment System

- Professional Learning

- Communications & Resources