Purpose: 	To create a “script” for your building/district implementation of the KCCS.

Directions: 	1. Using this form as a template, develop a work plan for each goal identified through

the needs assessment process. Modify the form as needed to fit your unique context.

Completing the form electronically allows cells of the chart to be expanded.

2. Distribute copies of the implementation plan to the members of the collaboration.

3. Keep copies handy to bring to meetings to review and update regularly. You may

decide to develop new plans for new phases of your implementation.

Goal:

Results/Accomplishments:

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources Resources Available Resources Needed (financial, human, political & other) | Potential Barriers What individuals or entities might resist? How do we address this resistance? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| Step 1: Hand out Common Core Standards to read and study the shifts and overview them. Concentrate on grade bands to study KCCS for them. Do crosswalking activity to compare old and new standards and current curriculum needs. | Headmaster | August 2012 inservices | A. Copies of standards B. Scavenger Hunt C. Video on Crosswalking activity | A. Time B. | Everyone, |
| Step 2: Discussions with and Observations of other teachers in specific strategies for KCCS. | Headmaster and Teachers | 1st nine weeks of 2012-2013 | A. Substitute Teachers B.Willing Districts | A. Finding districts that are ready for observations B. | All certified staff, observation, and 1 time per year |
| Step 3: Implementation of ELA Shifts 1, 4, and 6 | All teachers | Begin in August and continue throughout 2012-2013 | A. Beck’s 3 Tiers of Vocabulary, Bringing Words to life by Isabel Beck 1-57230-753-6 and Creating Robust Vocabulary by Isabel Beck 978-1-59385-753-0 B. More non-fiction materials c. Common Core Curriculum Maps by Teachers for teachers 978-1-118-10822-2 Jossey-Bass D. Training | A. Planning Time B. | All teachers, varied methods, bi-weekly staff meetings |
| Step 4: Implementation of critical areas in each grade level with the focus of Math Shifts 3, 4, and 6 | All Teachers | Begin in August and continue throughout 2012-2013 | A. Current Textbooks B. Internet C. Parents D. Time E. Manipulatives F. Training | A. Time | All teachers |
| Step 5: Implement ELA Shifts 2, 3, and 5 | All Teachers | Begin August 2013 | A. Document Cameras for Smartboards B. 6-Trait Rubrics C. Training | A.Time B. | All Teachers |
| Step 6: Begin work on the specific standards and begin to add the focuses of Math shifts 1, 2, and 5 | All Teacher | Begin in August 2013 | A. Current Curriculum B. Supplementals C. Training | A.Time B. | All Teachers |
| Step 7: Evaluate work samples to assess teacher and student progression Pre and post tests | Teachers and headmaster | Pretest in August 2012 and progress test periodically (Times to be determined) | A. Time to develop tests B. Timeline C. Goals | A. Knowledge for pretest B. Process is vague | All teachers |
| Step 8: Continued improvement and cycle | All Certified Staff | Bi-weekly | A. All of the above | A. Time | All teachers |

Evidence Of Success (How will you know that you are making progress? What are your benchmarks?)

Evaluation Process (How will you determine that your goal has been reached? What are your measures?)

# Text boxes

Implementation Component:

- Managing Change

X   Instructional Practices

- Curricula

- An Assessment System

X   Professional Learning

- Communications & Resources