Note: Berean is a private school, and as such, we are not required to implement KCCS; however, due to our commitment 
to educational excellence and accountability, we are using the KCCS as our basic curriculum, though we go beyond that 
with our emphasis on religious training and studies. Berean is accredited through ACSI (Association of Christian Schools 
International; our reaccreditation evaluation will take place in April or May of 2014. ACSI requires alignment of our curriculum with state standards.

Goal: To educate and provide resources for shifts in instructional practices of CCSS in Math and ELA

Results/Accomplishments: Incorporate KCCS in 7-12 (a broad plan) for 2012-13

Continuation and follow through in 2013-14 and 2014-15

| Action Steps What Will Be Done? | Responsibilities Who Will Do It? | Timeline By When? (Day/Month) | Resources Resources Available Resources Needed (financial, human, political & other) | Potential Barriers What individuals or entities might resist? How do we address this resistance? | Communications Plan Who is involved? What methods? How often? |
| --- | --- | --- | --- | --- | --- |
| Step 1: Inform administration of the steps needed to train staff | Arleta Wiebe | July/August | A. elements of power points from KCCS B. Arleta must develop power point and possible points to include in the in-service presentation. | A. (?) B. education & familiarity with the shifts to Common Core. Arleta must be knowledgeable enough to answer questions | 1. Arleta—presenter 2. administration (Terry, David, & Galen) 3. Invite a couple of key board members? Length of meeting: 2 hours. We can be flexible and meet more than once. |
| Step 2: Pre-school in-service: A. Present Common Core definition and purpose. B. Explanation of shifts—Briefly explain all shifts; focus on deeper explanation and examples of two shifts for ELA and two for Math C. “Habits of Mind” | Arleta | TBA: August 10, 13 or 14 (one to two hours) | A. power points—specific slides B. handouts based on power points | A. veteran teachers and/or teachers who teach subjects which may not see themselves as affected by KCCS (PE teachers? music teachers?) B. discussion | Involved: All teachers and staff Methods: Direct instruction followed by discussion How often: Initial in-service is one session of 1-2 hours |
| Step 3: Staff discussion and question time | Arleta | TBA: August 10, 13 or 14 | A. refer to power point and handouts B. | A. veteran teachers and/or teachers who teach subjects which may not see themselves as affected by KCCS (PE teachers? music teachers?) B. discussion/explanation/examples offered | All teachers, administration (perhaps a board member or two) will be involved. Arleta generates discussion questions and activities. |
| Step 4: Each staff member reads and becomes acquainted with KCCS. Divide into elementary groups and subject groups at JH and secondary. | Arleta/Staff | TBA: Initial: one hour at in-service Continuation at in-service meetings throughout year | A. copies of grade level common core and present curriculum guide B. need to make copies | A. confusion of teachers B. explanation | Arleta leads discussion / Staff works on Common Core and Curriculum Guide |
| Step 5: Instruction about shifts. Review Shifts 1 & 2, include Shift 3 (and maybe 4) Divide into elementary groups, JH and secondary subjects | Arleta & Kris?? David?? Staff | TBA: In-service in September?? | A. power point / examples B. | A. barrier: time! B. | Arleta &/or Kris give instruction, walk through examples, and lead discussion |
| Step 6: Include KCCS in Curriculum Guide | Arleta & Kris?? David?? Staff | 2012-13 and 2013-14 | A. copies of grade level common core and present curriculum guide | A. barrier: time! | Arleta &/or Kris give instruction, walk through examples, and lead discussion |
| Step 7: Define and show how to include Shifts 5 & 6 | Arleta/Kris?? David?? Staff | 2012-13 & 2013-14 | Examples / Discussion groups | A. barrier: time! | Arleta &/or Kris give instruction, walk through examples, and lead discussion |

Evidence Of Success (How will you know that you are making progress? What are your benchmarks?)

Progress will be shown through inclusion of shifts in lessons plans (for elementary), and observation (secondary).

Benchmarks:

Each teacher includes a shift question on each test administered.

Discussion: Each teacher contributes two examples of how shifts are included in lessons.

Observation by principal

Evaluation Process (How will you determine that your goal has been reached? What are your measures?): 
	Teacher survey conducted at semester and at end of year.

Observation by principals.

Interviews conducted by Arleta.

# Text boxes

Implementation Component:

- Managing Change

- Instructional Practices

- Curricula

- An Assessment System

- Professional Learning

- Communications & Resources